## Лист1
Task | Status | Deadline
Display categories | Done
Ability to add/remove category | Done
Display topics (sorted by categories) | Done
Ability to add/remove topic | Done | 2017-07-12
Adding new user | Done
Authentication and login | Done
Review topic | Done
Ability to add post into topic | Done
Ability to evaluate post | Done | 2017-07-19
Editing controllers and factories | Done
Adding input data validation | Done
Gulp workflow automating | Done | 2017-07-26
Ability to choose the best post | Done
Edit topic settings | Done
Change topic category | Done | 2017-08-02
Edit post | Done
Time limitation to edit personal post | Done | 2017-08-09
Review profile | Done
Block/unblock user | Done | 2017-08-16
Roles (admin, user, guest) | Done | 2017-08-23
Review, Refactor, Troubleshooting | Open | 2017-08-30